## Sprint
|  |  |  | Week #1 (10 hrs / week) | [6 empty] | Week #2 (10 hrs / week) | [6 empty] | Week #3 (10 hrs / week) | [6 empty] | Week #4 (10 hrs / week)
Backlog Item | Task | Task Owner | Initial Estimate (Total Sprint Hours = 40 x 6) | D1 | D2 | D3 | D4 | D5 | D6 | D7 | D8 | D9 | D10 | D11 | D12 | D13 | D14 | D15 | D16 | D17 | D18 | D19 | D20 | D21 | D22 | D23 | D24 | D25 | D26 | D27 | D28
|  |  |  | 2014-09-13 | 2014-09-14 | 2014-09-15 | 2014-09-16 | 2014-09-17 | 2014-09-18 | 2014-09-19 | 2014-09-20 | 2014-09-21 | 2014-09-22 | 2014-09-23 | 2014-09-24 | 2014-09-25 | 2014-09-26 | 2014-09-27 | 2014-09-28 | 2014-09-29 | 2014-09-30 | 2014-10-01 | 2014-10-02 | 2014-10-03 | 2014-10-04 | 2014-10-05 | 2014-10-06 | 2014-10-07 | 2014-10-08 | 2014-10-09 | 2014-10-10
|  |  |  | 240 | 231 | 222 | 213 | 204 | 195 | 186 | 177 | 168 | 159 | 150 | 141 | 132 | 123 | 114 | 105 | 96 | 87 | 78 | 69 | 60 | 51 | 42 | 33 | 24 | 15 | 6 | 0 | Ideal Burndown
|  |  | 240 | 2014-09-13: 200; 2014-09-14: 193; 2014-09-15: 188; 2014-09-16: 195; 2014-09-17: 200; 2014-09-18: 207; 2014-09-19: 184; 2014-09-20: 175; 2014-09-21: 167; 2014-09-22: 151; 2014-09-23: 130 | Remaining Hrs (Total)
Create 2 user stories each - one technical story for Design Pattern - 2nd story should be about a feature in the Game | Technical story for a design pattern | Megha | 40 | 2014-09-13: 40; 2014-09-14: 40; 2014-09-15: 40; 2014-09-16: 38; 2014-09-17: 34; 2014-09-18: 32; 2014-09-19: 30; 2014-09-20: 28; 2014-09-21: 27; 2014-09-22: 25; 2014-09-23: 20
| Story about a feature in the game | Megha | 20 | 2014-09-13: 20; 2014-09-14: 20; 2014-09-15: 20; 2014-09-16: 20; 2014-09-17: 20; 2014-09-18: 20; 2014-09-19: 10; 2014-09-20: 9; 2014-09-21: 8; 2014-09-22: 7; 2014-09-23: 6
| Technical story for a design pattern | Anjali | 40 | 2014-09-13: 40; 2014-09-14: 38; 2014-09-15: 38; 2014-09-16: 37; 2014-09-17: 36; 2014-09-18: 35; 2014-09-19: 34; 2014-09-20: 33; 2014-09-21: 32; 2014-09-22: 31; 2014-09-23: 30
| Story about a feature in the game | Anjali | 20 | 2014-09-13: 20; 2014-09-14: 15; 2014-09-15: 10; 2014-09-16: 20; 2014-09-17: 30; 2014-09-18: 40; 2014-09-19: 30; 2014-09-20: 25; 2014-09-21: 20; 2014-09-22: 8; 2014-09-23: 4
| Technical story for a design pattern | Chirag | 20 | 2014-09-13: 20; 2014-09-14: 20; 2014-09-15: 20; 2014-09-16: 20; 2014-09-17: 20; 2014-09-18: 20; 2014-09-19: 20; 2014-09-20: 20; 2014-09-21: 20; 2014-09-22: 20; 2014-09-23: 10
| Story about a feature in the game | Chirag | 20 | 2014-09-13: 20; 2014-09-14: 20; 2014-09-15: 20; 2014-09-16: 20; 2014-09-17: 20; 2014-09-18: 20; 2014-09-19: 20; 2014-09-20: 20; 2014-09-21: 20; 2014-09-22: 20; 2014-09-23: 20
| Technical story for a design pattern | Saumil | 40 | 2014-09-13: 40; 2014-09-14: 40; 2014-09-15: 40; 2014-09-16: 40; 2014-09-17: 40; 2014-09-18: 40; 2014-09-19: 40; 2014-09-20: 40; 2014-09-21: 40; 2014-09-22: 40; 2014-09-23: 40
| Story about a feature in the game | Saumil
| Technical story for a design pattern | Marianne
| Story about a feature in the game | Marianne
Create UI Wireframes
Create UML Analysis Models
Create Domain Model Diagram
Team:
Megha | 10 hours / Week
Anjali | 10 hours / Week
Saumil | 10 hours / Week
Chirag | 10 hours / Week
Marianne | 10 hours / Week
Total Available Hours During Sprint: | 240